## Sheet1
Description | Type | Status | Quantity for 1 Assembly | Quantity for 10 Assemblies | Quantity for 50 Assemblies | Quantity @ Bates | Quantity to Purchase | Github File | Manufacturer | Manufacturer Part # | Vendor 01 | Vendor 01 Part # | Vendor 01 Cost | Cost for 50 | Vendor 01 Ready to Ship | Vendor 01 Lead Time (weeks) | Vendor 02 | Vendor 02 Cost | Vendor 02 Ready to Ship | Lead Time (weeks) | Vendor 02 | Vendor 02 Cost | Vendor 02 Ready to Ship | Vendor 02 Lead Time (weeks)
Khatod 1825 silicone optic | Stock Part | Validated | 6 | 60 | 300 |  |  | 1621-1007-ND_KHATOD OPTIC 1825 | Khatod | PL1825SR | Digikey | 1621-1007-ND | 17.97 | 5391 | 16 | 8 |  |  |  |  | Khatod | pending response | pending response | pending response
12" heat sink | Stock Part | Validated | 1 | 10 | 50 |  |  | 416201U00000G-ND_12IN HEATSINK | Aavid | 416201U00000G | Digikey | 416201U00000G-ND | 83.72 | 4186 | 92 | 8 |  |  |  |  | Mouser | 80.73 | 59 | 10
COB Driver | Stock Part | In Design | 1 | 10 | 50 |  |  | 1800-1101-ND_ERP DRIVER | ERP | SLM160W-3.9-40-ZA | Digikey | 1866-2579-ND | 169 | 8450 | 9 | 6 |  |  |  |  | Mouser | 50.09 | 50 | 12
Vero SE 5000K COB LED | Stock Part | Validated | 2 | 20 | 100 |  |  | 976-1596-ND_BRIDGELUX VERO29 | Bridgelux | BXRC-50C10K1-D-74-SE | Digikey | 976-1596-ND | 22.98 | 2298 | 1699 | 6
Vero SE 3000K COB LED | Stock Part | Validated | 2 | 20 | 100 |  |  | 976-1596-ND_BRIDGELUX VERO29 | Bridgelux | BXRC-30E10K0-D-73-SE | Digikey | 976-1590-ND | 22.98 | 2298 | 423 | 6
1" x 3' x 1/16" 40A neoprene rubber strip (side gasket) | Stock Material | In Design | 1 | 10 | 50 |  |  | lhc-320 | not listed | not listed | McMaster Carr | 1376N13 | 10.38 | 519 | not listed, ready | not listed, ready
.09" x 48" x 48" aluminum plate (mounting plate) | Stock Material | In Testing | 0.066667 | 0.66667 | 3.3333 |  |  | lhc-319 | not listed | not listed | McMaster Carr | 89015K59 | 191.8 | 639.3333 | not listed, ready | not listed, ready
3/16" x 48" x 36" ABS REQUOTE | Stock Material | In Testing | 0.05 | 0.5 | 2.5 |  |  | lhc-321 | not listed | not listed | McMaster Carr | 8505K753 | 99.41 | 248.525 | not listed, ready | not listed, ready
4-40 x 1/8" screw (box of 100) | Stock Part | Validated | 0.12 | 1.2 | 6 |  |  |  | not listed | not listed | McMaster Carr | 91773A103 | 8.26 | 49.56 | not listed, ready | not listed, ready
6-32 x 7/8" bolt (box of 100) | Stock Part | Validated | 0.04 | 0.4 | 2 |  |  |  | not listed | not listed | McMaster Carr | 92949A152 | 6.22 | 12.44 | not listed, ready | not listed, ready
6-32 nuts (box of 100) | Stock Part | Validated | 0.04 | 0.4 | 2 |  |  |  | not listed | not listed | McMaster Carr | 90257A007 | 6.75 | 13.5 | not listed, ready | not listed, ready
6-32 belleville washer (box of 100) | Stock Part | Validated | 0.04 | 0.4 | 2 |  |  |  | not listed | not listed | McMaster Carr | 90127A007 | 8.5 | 17 | not listed, ready | not listed, ready
8-32 x 7/8" bolt (box of 100) | Stock Part | In Design | 0.1 | 1 | 5 |  |  |  | not listed | not listed | McMaster Carr | 92949A198 | 8.09 | 40.45 | not listed, ready | not listed, ready
8-32 thumb nut (pack of 10) | Stock Part | In Design | 0.2 | 2 | 10 |  |  |  | not listed | not listed | McMaster Carr | 93886A120 | 8.03 | 80.3 | not listed, ready | not listed, ready
Plastic-metal hydronic fittings | Stock Part | Validated | 2 | 20 | 100 |  |  | 9406T170_PUSH-TO-CONNECT TUBE FITTING FOR SS TUBING |  |  | McMaster Carr | 9406T170 | 6.45 | 645
Quick-disconnect tube coupling, socket | Stock Part | In Design | 2 | 20 | 100 |  |  |  | not listed | not listed | McMaster Carr | 51545K73 | 18.63 | 1863 | not listed, ready | not listed, ready
Quick-disconnect tube coupling, plug | Stock Part | In Design | 2 | 20 | 100 |  |  |  | not listed | not listed | McMaster Carr | 51545K79 | 13.55 | 1355 | not listed, ready | not listed, ready
3/8" OD, 1/4" ID x 1' PVC tubing | Stock Part | Validated | 20 | 200 | 1000 |  |  | 5648K263_CHOOSE-A-COLOR POLYURETHANE TUBING | not listed | not listed | McMaster Carr | 5233K56 | 0.28 | 280 | not listed, ready | not listed, ready
Heatsink compound | Stock Material | Validated | 0.04 | 0.4 | 2 |  |  |  | MoneyQiu | B07H1PGY7X | Amazon | B07H1PGY7X | 9.99 | 19.98 | not listed, ready | not listed, ready
Glycol | Stock Material | Validated |  | 0
2-conductor wire | Stock Material | Validated |  | 0
7-pole plug | Stock Material | In Design | 1 | 10 | 50 |  |  | 3216K670_HARSH ENVIRONMENT MINI CONNECTOR | not listed | not listed | Digikey | C01630G00610012 | 9.13 | 456.5 | not listed, ready | not listed, ready
Mounting arm REQUOTE | Stock Part | In Design | 1 | 10 | 50 |  |  |  | Fleximount | M09 / M17 | Fleximount |  | 60 | 3000 |  | not listed, ready
Custom metal enclosure | Custom Part | In Design | 1 | 10 | 50 |  |  | lhc-322 | pending | custom |  |  | 26 | 1300
Custom end cap | Custom Part | In Design | 2 | 20 | 100 |  |  | lhc-317 | pending | custom
Far red LED | Stock Part | In Design | 2 | 20 | 100
Far red LED Driver
Delrin or metal mounting bracket, back of enclosure | Custom Part | In Design | 1 |  | 50 | [7 empty] | 12 | 600
TOTAL COST: | [12 empty] | 808.12 | 33162.5883